## Task_Table1
JAN DE NUL GROUP
| Author: | David De Boom
Last Saved:
| Revision: | 1
|  | Total Amount of Activities: | 38
Project: |  | Done: | 0
|  |  | 0 | %
Activity | Location | Who | OT Act. | Done? | Date | Executed By | Remarks
Planning phase
Create Request ticket in Omnitracker | Aalst | TSE / Req Admin | YES |  |  |  |  | FALSE
Create Copy of Checklist | Aalst | TSE | YES |  |  |  |  | FALSE
Site survey |  |  | YES
Equipment required | Site / Ship / Aalst | TSE | [5 empty] | FALSE
Applications used | Site / Ship / Aalst | TSE | [5 empty] | FALSE
Locations of data to migrate | Site / Ship / Aalst | TSE | [5 empty] | FALSE
Site changes (wiring,racks,…) | Site / Ship / Aalst | TSE | [5 empty] | FALSE
Special requests | Site / Ship / Aalst | TSE | [5 empty] | FALSE
Site specifics (secure, shared, runtime, no. Users, bandwith, latency) | Site / Aalst | TSE | [5 empty] | FALSE
Design proposal |  |  | YES
Create proposal based on deployment guidelines | Aalst | TSE | [5 empty] | FALSE
Request approval of design | Aalst | TSE | YES |  |  |  |  | FALSE
Team Lead TSE & SA/SE | Aalst | TSE | [5 empty] | FALSE
IT Mgmt | Aalst | TSE | [5 empty] | FALSE
TD | Aalst | TSE | [5 empty] | FALSE
Stock reservation |  |  | YES
Creation of requestform (AVB) | Aalst | ICT-PURCHASE | [5 empty] | FALSE
Check current stock | Aalst | TSE / Stock Manager | [5 empty] | FALSE
Reserve required assets | Aalst | TSE / Stock Manager | [5 empty] | FALSE
Order missing assets | Aalst | TSE / Stock Manager | [5 empty] | FALSE
Roll-out plan |  |  | YES
Request assets | Aalst | TSE | [5 empty] | FALSE
Create time line | Aalst | TSE | [5 empty] | FALSE
Request approval of roll-out plan | Aalst | TSE | YES |  |  |  |  | FALSE
Team Lead TSE & SA/SE | Aalst | TSE | [5 empty] | FALSE
IT Mgmt | Aalst | TSE | [5 empty] | FALSE
TD | Aalst | TSE | [5 empty] | FALSE
Installation phase
Create temp file for paswords \\jdn-file01\alg_inf\2. Projects\Technical Support\Nieuwe standaarden - documentatie | Aalst | TSE | [5 empty] | FALSE
Choose IP Range | Aalst |  | YES
Excel file firewall config | Aalst | TSE | [5 empty] | FALSE
IP Ranger | Aalst | TSE | [5 empty] | FALSE
If site | Aalst | TSE | YES
Determine Domain Controller Setup (see manual) | Aalst | TSE | [5 empty] | FALSE
If jandenul.com integrated |  |  | YES |  |  |  |  | FALSE
Request AD preparation by SA | Aalst | TSE | [5 empty] | FALSE
If Case Small Setup use coloured UTP cables !! | Aalst
Install & Configure Switches and Firewall |  |  | YES |  |  |  |  | FALSE
Fill out xls file (see manual) | Aalst | TSE | [5 empty] | FALSE
Install & configure switch stack | Aalst | TSE | [5 empty] | FALSE
Configure SW (see manual) | Aalst | TSE | [5 empty] | FALSE
Install & configure firewall(s) | Aalst | TSE | [5 empty] | FALSE
Add to Remote desktop manager | Aalst | TSE | [5 empty] | FALSE
Configure FW (see manual) | Aalst | TSE | [5 empty] | FALSE
Connect the cables (view xls) | Aalst | TSE | [5 empty] | FALSE
Create ticket for SE to add FW/SW to Junos Space (assure that VPN is up) | Aalst | SE Ticketnr: SR- | YES |  |  |  |  | FALSE
IPMonitor Create new Ping VSAT <Vessel> - IP new firewall | Aalst | SE
If Large OR Medium setup then
Create config file with config generator file
Install & configure VRTX |  |  | YES
CMC | Aalst | TSE
SPERC | Aalst | TSE
Run Linux iso to upgrade the firmware of the system | Aalst | TSE
If Dell R430 | Aalst
Create config file with config generator file | Aalst
Install & Configure Dell R430 | Aalst | TSE | YES
Run Linux iso to upgrade the firmware of the system | Aalst | TSE
Install & configure blades | Aalst |  | YES
Label the blades (1-2-3) | Aalst | TSE
iDRAC with generated config | Aalst | TSE
ESXi with bootable stick | Aalst | TSE
If HPE DL20 | Aalst
Install HPE DL20 | Aalst | TSE
Configure ILO | Aalst | TSE
Configure and install ESX | Aalst | TSE
Deploy DC VM |  |  | YES
Run Installation script StartThisElevated.ps1 | Aalst | TSE
Copy the configuration scripts to the Scripts folder of the DC | Aalst | TSE
Edit config.xml with the installation parameters | Aalst | TSE
Run configuration script MainScript.ps1 | Aalst | TSE
Create ticket for SE to add domain in JDN as DNS forwarder | Aalst | SE Ticketnr: SR- | YES
Install & configure vCenter 6.5 |  |  | YES
Edit the JDN_vCSA_v1_1.json file | Aalst | TSE
Check if vCenter's FQDN is resolvable to IP | Aalst | TSE
Deploy vCenter appliance with StartThisElevated.ps1 | Aalst | TSE
Check if vSphere cluster is created | Aalst | TSE
Configure vCenter as per procedure | Aalst | TSE
Configure vSphere Appliance Management administrator account password to never expire | Aalst | TSE
Upload data to vSphere Datastore 01 |  |  | YES
Template/OVA deployment with StartThisElevated.ps1 | Aalst | TSE
Upload necessary Software ISOs | Aalst | TSE
Deploy pihole server
configure pihole accounts and password | Aalst | TSE
update pihole to latest version | Aalst | TSE
Deploy management VM | Aalst | TSE | YES
Set static IP for the 2nd network card | Aalst | TSE
Install latest RSAT tools | Aalst | TSE
Push latest VMRC | Aalst | TSE
Manually add servers to correct OU | Aalst | TSE
Install Teamviewer host (if not JDN integrated) | Aalst | TSE
Import data into Remote Desktop Manager |  | TSE
Domain maintenance |  |  | YES
Review created users | Aalst | TSE
Move users to correct OU | Aalst | TSE
Move servers to correct OUs | Aalst | TSE
Move MGMT to Managed Light | Aalst | TSE
Move clients to correct OUs | Aalst | TSE
Remove descriptions | Aalst | TSE
Add users to Remote Desktop Manager | Aalst | TSE
Deploy tasks VM | Aalst |  | YES
Initialise E-drive | Aalst | TSE
Install Altiris NS with Site Server Deployment workflow (see manual) | Aalst | TSE
All packages have status Ready | Aalst | TSE
Verify all windows servers will receive the altiris ns agent | Aalst | TSE
Deploy fileserver VM |  |  | YES
Initialize D-drive | Aalst | TSE
Run configuration script MainScript.ps1 | Aalst | TSE
Install Eset 6.5 (file security) - manual installation | Aalst | TSE
Deploy apps VM |  |  | YES
Initialize E-drive | Aalst | TSE
Run configuration script MainScript.ps1 | Aalst | TSE
Install Teamviewer host | Aalst | TSE
Install required applications | Aalst | TSE
Install Amos with the Amos server installation manual (Meso) | Aalst | TSE
Install and configure IRIS Management (see manual) | Aalst | TSE
Install & configure Synology Backup NAS(es) |  |  | YES
Backup Synology should have 8TB disks (VRTX only) | Aalst | TSE
Label the NAS(es) | Aalst | TSE
Update to latest DSM | Aalst | TSE
Configure the Synology NAS(s) (see Backup Synology manual) | Aalst | TSE
Install & configure Synology Machine NAS(es) |  |  | YES
Label the NAS(es) | Aalst | TSE
Update to latest DSM | Aalst | TSE
Configure the Synology NAS(s) (compare Backup Synology manual with Machine Synology manual) | Aalst | TSE
Configure BTRFS and snapshots | Aalst | TSE
Deploy backup VM |  |  | YES
Install Veeam 9.5 with Updates | Aalst | TSE
Configure Veeam with configuration script ConfigureVeeam9.5File.ps1 (see manual) | Aalst | TSE
For sites: check backups in Backupmanager / For ships: check backup mails in Commbox | Aalst | TSE
Deploy Commbox VM (only for ships) |  |  | YES
Configure Commbox (do not endanger production) (see manual) | Aalst | TSE
Deploy monitoring VM |  |  | YES
Deploy PRTG configuration (see manual) | Aalst | TSE
Create scheduled task with snapshot script | Aalst | TSE
Install UPS(es) |  |  | YES
Configure UPS (see manual) | Aalst | TSE
Deploy Powerchute VM |  |  | YES
Set new administrator password in VM | Aalst | TSE
Configure Powerchute | Aalst | TSE
Perform UPS callibration & self-test | Aalst
Check Battery | Aalst | TSE
Test automatic shutdown of vm's | Aalst | TSE
Deploy ESETPXY vm |  |  | YES
Configure VM with web interface | Aalst | TSE
Install and configure ESET on fileserver | Aalst | TSE
Configure Autostart | Aalst | TSE
Install & Configure 4G modem |  | TSE | YES
Install & Configure Access Points |  | TSE | YES
Edit the configuration in Aruba-Dell-IAP.xlsx (see manual) | Aalst | TSE
If ship configure wifi.local certificate | Aalst | TSE
Update firmware | Aalst | TSE
Install & Configure Time Server (only for ships) |  | TSE | YES
Update firmware and upload configuration (see manual) | Aalst | TSE
Configure Automatic boot order of virtual machines |  | TSE
Enable Database Retention Policy |  | TSE
Deploy clients |  |  | YES
Deploy Fat clients | Aalst | HW Deployers
Deploy Thin clients | Aalst | TSE
Deploy VM (only for ships) | Aalst | TSE
Create users | Aalst | TSE
Create RDP Desktop shortcuts on fat clients | Aalst | TSE
Move server to correct OU | Aalst | TSE
Outlook: import global address list Jan De Nul CSV-file | Aalst | TSE
Deploy software through Altiris NS | Aalst | TSE/SA (non-domain) | YES
Check if installed software is compliant with site survey on every client vm | Aalst | TSE
Install Teamviewer host on Amos VM | Aalst | TSE
Install Windows updates on all clients and servers |  | TSE
Deploy Printers
For MFP printers configure and test Scan 2 Folder (see manual) | Aalst | TSE
Deploy labelprinters
Configure labelprinters on all clent VMs | Aalst | TSE
If offshore configure Moxa nPort (only for ships) |  | TSE | YES
IT Manual |  |  | YES
Compile via Latex | Aalst | TSE
Upload to Meso | Aalst | TSE
Upload to IT_PUB | Aalst | TSE
Pre-Shipping phase
Check Site changes (wiring,racks,…) | Aalst | TSE
Quality control checklist 1 | Aalst | TSE Install | YES
Quality control checklist 2 | Aalst | TSE Project | YES
Smoke Tests | Aalst | TSE/SSE/SA/SE/DEV | YES
Disbale VPN before shipping | Aalst | SA/SE | YES
Prepare for shipping | Aalst | TSE | YES
Finish request form (AVB) | Aalst | ICT-PURCHASE
Shipping checklist | Aalst | TSE | YES
Validate migration procedures |  |  | YES
File server data | Aalst | TSE
Commbox (only for ships) | Aalst | TSE
Comm-E | Aalst | TSE
User data | Aalst | TSE
Ship hardware | Aalst | TSE/PURCHASE/Stock manager | YES
Before departure
Warn SSE to change replication from old commbox to SFTP (give date of conversion) | Aalst | TSE
Change replication from old commbox to SFTP | Aalst | SSE | YES
Warn SA to change settings for mail routing on Exchange and Ironport (give date of conversion) | Aalst | TSE
Warn Speedcast to make changes to the routers | Aalst | TSE
Installation on Site
Equipment check | Ship / Site | TSE | YES
Site changes check (wiring, racks,…) | Ship / Site | TSE | YES
Migration preparation |  |  | YES
File server data | Ship / Site | TSE
Comm-E | Ship / Site | TSE
User data | Ship / Site | TSE
Shut down current environment (Not the Commbox!) | Ship / Site | TSE | YES
Rack & patch |  |  | YES
Switches | Ship / Site | TSE
Firewall(s) | Ship / Site | TSE
Server | Ship / Site | TSE
UPS | Ship / Site | TSE
Nas | Ship / Site | TSE
Moxa nPort (if applicable) | Ship / Site | TSE
Boot physical systems |  |  | YES
Switch stack | Ship / Site | TSE
Firewall(s) | Ship / Site | TSE
UPS | Ship / Site | TSE
VRTX | Ship / Site | TSE
Blades | Ship / Site | TSE
Synologies | Ship / Site | TSE
Moxa nPort (if applicable) | Ship / Site | TSE
Boot VMs |  |  | YES
Log into ESXi, find vCenter & boot it up | Ship / Site | TSE
Verify that all ESXi rejoin the cluster | Ship / Site | TSE
Boot VMs through the vCenter | Ship / Site | TSE
Mgmt | Ship / Site | TSE
DC | Ship / Site | TSE
Proxy | Ship / Site | TSE
Commbox (check procedure) (only for ships)
Close outlook clients on old clients | Ship / Site | TSE
Change settings Exchange | Aalst | SA/SE | YES
Change settings Ironport | Aalst | SA/SE | YES
Remove settings from old commbox headoffice | Ship / Site | SA/SE | YES
Open outlook clients on old clients to get last mails from old commbox | Ship / Site | TSE
Shut down old commbox | Ship / Site | TSE
Start new virtual commbox | Ship / Site | TSE
Open outlook clients on new clients and test mailing | Ship / Site | TSE
Warn SSE to change replication from SFTP to new commbox | Ship / Site | TSE
Change replication from SFTP to new commbox | Aalst | SSE | YES
Test replication over new virtual vessel commbox | Ship / Site | TSE
File | Ship / Site | TSE
Tasks | Ship / Site | TSE
Apps (check procedure) | Ship / Site | TSE
Backup | Ship / Site | TSE
UPSmgmt | Ship / Site | TSE
Migrate data |  |  | YES
File server data | Ship / Site | TSE
User data | Ship / Site | TSE
Client installation | Ship / Site | TSE | YES
Thin client installation | Ship / Site | TSE | YES
WiFi installation | Ship / Site | TSE
Handscanner (+wifi) installation | Ship / Site | TSE | YES
Install Validation Phase
Network testing | Ship / Site | TSE | YES
Application testing |  |  | YES
Test Amos on all clients | Ship / Site | TSE
Test login | Ship / Site | TSE
Test label printer | Ship / Site | TSE
Task Server - Check ESET downloads | Ship / Site | TSE
Task Server - Check NS communication | Ship / Site | TSE
Crew testing | Ship / Site | TSE | YES
Handover phase
Crew briefing |  |  | YES
Routine use | Ship / Site | TSE
Emergency procedures | Ship / Site | TSE
ICE kit usage | Ship / Site | TSE
Handover documentation
Crew | Ship / Site | TSE | YES
IT Ops | Ship / Site | TES | YES
Adjust data in Remote Desktop Manager | Ship / Site | TSE | YES
Dell |  |  | YES
Notify Dell of deployment and expected working region | Aalst | TSE
To Do's | Aalst
Handover document TSE Ticketing
Create ticket with open issues | Aalst | TSE | YES
Old Firewall (in case of replacement) | Aalst
Discontinue the service contract on the SSG firewall | Aalst | ICT-PURCHASE | YES
Clear the config of the firewall/Switches | Aalst | TSE | YES
Remove VPN settings on central FW | Aalst | SA/SE | YES
Remove from ipranger | Aalst | SA/SE | YES
Remarks / To do's